## Sheet1
Times | Date | Planned | Actual | Sprint 1 Backlog:
Thu | 2002-02-01 | 9 | 9 | Setup Repo and Unity
Fri | 2003-02-01 | 7 | 8 | Install and configure Antlr4
Sat | 2004-02-01 | 5 | 8 | Create Main Menu
Sun | 2005-02-01 | 4 | 6 | Create Script Editor
Mon | 2006-02-01 | 3 | 2 | Create Script
Tue | 2007-02-01 | 2 | 0 | Save Script
Wed | 2008-02-01 | 1 | 0 | Delete Script
Thu | 2009-02-01 | 0 | 0 | Edit Script
Create Language Grammar
Times | Date | Planned | Actual | Sprint 2 Backlog:
Fri | 2010-02-01 | 6 | 6 | Design and create thread scheduling algorithm
Sat | 2011-02-01 | 6 |  | Connect Lexer and Parser to IDE
Sun | 2012-02-01 | 6 |  | Build AST from scripts on play
Mon | 2013-02-01 | 5 |  | Set character class
Tue | 2014-02-01 | 5 |  | Create execution model
Wed | 2015-02-01 | 5 |  | Integrate interpreter into scripts
Thu | 2016-02-01 | 4
Fri | 2017-02-01 | 4
Sat | 2018-02-01 | 4
Sun | 2019-02-01 | 3
Mon | 2020-02-01 | 3
Tue | 2021-02-01 | 2
Wed | 2022-02-01 | 2
Thu | 2023-02-01 | 1
Fri | 2024-02-01 | 1