## Sheet1
Times | Date | Planned | Actual | Sprint 1 Backlog:
Thu | 2023-02-02 | 9 | 9 | Setup Repo and Unity
Fri | 2023-02-03 | 7 | 8 | Install and configure Antlr4
Sat | 2023-02-04 | 5 | 8 | Create Main Menu
Sun | 2023-02-05 | 4 | 6 | Create Script Editor
Mon | 2023-02-06 | 3 | 2 | Create Script
Tue | 2023-02-07 | 2 | 0 | Save Script
Wed | 2023-02-08 | 1 | 0 | Delete Script
Thu | 2023-02-09 | 0 | 0 | Edit Script
Create Language Grammar
Times | Date | Planned | Actual | Sprint 2 Backlog:
Fri | 2023-02-10 | 6 | 6 | Design and create thread scheduling algorithm
Sat | 2023-02-11 | 6 | 5 | Connect Lexer and Parser to IDE
Sun | 2023-02-12 | 6 | 4 | Build AST from scripts on play
Mon | 2023-02-13 | 5 | 2 | Set character class
Tue | 2023-02-14 | 5 | 2 | Create execution model
Wed | 2023-02-15 | 5 | 1 | Integrate interpreter into scripts
Thu | 2023-02-16 | 4 | 1
Fri | 2023-02-17 | 4 | 1
Sat | 2023-02-18 | 4 | 1
Sun | 2023-02-19 | 3 | 1
Mon | 2023-02-20 | 3 | 0
Tue | 2023-02-21 | 2
Wed | 2023-02-22 | 2
Thu | 2023-02-23 | 1
Fri | 2023-02-24 | 0
Times | Date | Planned | Actual | Sprint 3 Backlog:
Fri | 2023-02-24 | 7 | 7 | Create Character objects in game
Sat | 2023-02-25 | 7 | 5 | Play simulation
Sun | 2023-02-26 | 6 | 5 | Pause, Stop, and Step Simulation
Mon | 2023-02-27 | 6 |  | Instruction Cost Visualisation
Tue | 2023-02-28 | 5 |  | Scheduler Representation
Wed | 2023-03-01 | 5 |  | Pause Menu
Thu | 2023-03-02 | 4 |  | Camera Movement
Fri | 2023-03-03 | 4
Sat | 2023-03-04 | 3
Sun | 2023-03-05 | 3
Mon | 2023-03-06 | 2
Tue | 2023-03-07 | 2
Wed | 2023-03-08 | 1
Thu | 2023-03-09 | 1
Fri | 2023-03-10 | 0