## Burndown
Times | Date | Planned | Actual | Sprint 1 Backlog:
Thu | 2023-02-02 | 9 | 9 | Setup Repo and Unity
Fri | 2023-02-03 | 7 | 8 | Install and configure Antlr4
Sat | 2023-02-04 | 5 | 8 | Create Main Menu
Sun | 2023-02-05 | 4 | 6 | Create Script Editor
Mon | 2023-02-06 | 3 | 2 | Create Script
Tue | 2023-02-07 | 2 | 0 | Save Script
Wed | 2023-02-08 | 1 | 0 | Delete Script
Thu | 2023-02-09 | 0 | 0 | Edit Script
Create Language Grammar
Times | Date | Planned | Actual | Sprint 2 Backlog:
Fri | 2023-02-10 | 6 | 6 | Design and create thread scheduling algorithm
Sat | 2023-02-11 | 6 | 5 | Connect Lexer and Parser to IDE
Sun | 2023-02-12 | 6 | 4 | Build AST from scripts on play
Mon | 2023-02-13 | 5 | 2 | Set character class
Tue | 2023-02-14 | 5 | 2 | Create execution model
Wed | 2023-02-15 | 5 | 1 | Integrate interpreter into scripts
Thu | 2023-02-16 | 4 | 1
Fri | 2023-02-17 | 4 | 1
Sat | 2023-02-18 | 4 | 1
Sun | 2023-02-19 | 3 | 1
Mon | 2023-02-20 | 3 | 0
Tue | 2023-02-21 | 2 | 0
Wed | 2023-02-22 | 2 | 0
Thu | 2023-02-23 | 1 | 0
Fri | 2023-02-24 | 0 | 0
Times | Date | Planned | Actual | Sprint 3 Backlog:
Fri | 2023-02-24 | 7 | 7 | Create Character objects in game
Sat | 2023-02-25 | 7 | 5 | Play simulation
Sun | 2023-02-26 | 6 | 5 | Pause, Stop, and Step Simulation
Mon | 2023-02-27 | 6 | 5 | Instruction Cost Visualisation
Tue | 2023-02-28 | 5 | 5 | Scheduler Representation
Wed | 2023-03-01 | 5 | 5 | Pause Menu
Thu | 2023-03-02 | 4 | 4 | Camera Movement
Fri | 2023-03-03 | 4 | 2
Sat | 2023-03-04 | 3 | 2
Sun | 2023-03-05 | 3 | 1
Mon | 2023-03-06 | 2 | 1
Tue | 2023-03-07 | 2 | 1
Wed | 2023-03-08 | 1 | 1
Thu | 2023-03-09 | 0 | 0
Times | Date | Planned | Actual | Sprint 4 Backlog:
Fri | 2023-03-10 | 9 | 9 | Create Skirmish Battle
Sat | 2023-03-11 | 9 | 8 | Customise Skirmish Battle
Sun | 2023-03-12 | 8 | 7 | Battle Model
Mon | 2023-03-13 | 7 | 5 | Rescheduling
Tue | 2023-03-14 | 7 | 5 | Message passing
Wed | 2023-03-15 | 6 | 4 | Yielding
Thu | 2023-03-16 | 6 |  | Character Death
Fri | 2023-03-17 | 5 |  | End Game Victory / Defeat
Sat | 2023-03-18 | 4 |  | Health Bars
Sun | 2023-03-19 | 4
Mon | 2023-03-20 | 3
Tue | 2023-03-21 | 2
Wed | 2023-03-22 | 1
Thu | 2023-03-23 | 0

## SchedulerAnalysis
For all tests, the values not being tested will take their default value
MinQueueTime | Average Wait Time | Average Processor Steps | MaxQueueTime | Average Wait Time | Average Processor Steps | NumCores | Average Wait Time | Average Processor Steps | NumCharacters | Average Wait Time | Average Processor Steps
1 | 6.0652 | 252.1726 | 10 | 5.7827 | 251.5627 | 1 | 12.4242 | 84.1156 | 1 | 0.902 | 457.07
2 | 6.4818 | 252.1835 | 11 | 6.1718 | 251.7405 | 2 | 11.9082 | 168.1952 | 2 | 0.899 | 456.9835
3 | 6.886 | 252.2138 | 12 | 6.513 | 251.8399 | 3 | 7.6788 | 252.3895 | 3 | 0.9 | 457.0947
4 | 7.2637 | 252.2774 | 13 | 6.8957 | 252.0646 | 4 | 4.2098 | 336.1249 | 4 | 2.9343 | 374.5405
5 | 7.6423 | 252.3678 | 14 | 7.2617 | 252.184 | 5 | 1.82 | 412.6183 | 5 | 5.436 | 302.6579
6 | 8.0007 | 252.4399 | 15 | 7.6102 | 252.2544 | 6 | 0.907 | 457.0397 | 6 | 7.6507 | 252.2825
7 | 8.3815 | 252.5263 | 16 | 7.9607 | 252.441 | 7 | 0.90283 | 457.0405 | 7 | 9.3989 | 216.2863
8 | 8.7472 | 252.5937 | 17 | 8.314 | 252.6368 | Default: 3 |  |  | 8 | 10.7912 | 189.27
9 | 9.0485 | 252.6224 | 18 | 8.6245 | 252.8199 |  |  |  | 9 | 11.8984 | 168.2153
10 | 9.342 | 252.7851 | 19 | 8.8903 | 252.9454 |  |  |  | 10 | 12.7038 | 151.3714
Default: 5 |  |  | 20 | 9.2603 | 253.1121 |  |  |  | 11 | 13.4237 | 137.6562
|  |  | Default: 15 | [5 empty] | 12 | 13.8078 | 126.1688
Default: 6